| Client | DEMO – Sample Process Plant (not a real client) | Contract / PO | DEMO-PC0001 |
| --- | --- | --- | --- |
| Project | Demo boiler shutdown inspection | Site | Demo Utilities Area |
| Report number | ES/DEMO-PC0001-DPR-003 | Date | 09 Oct 2026 |
| Day | 3 | Hours worked | 20 |

1. MANPOWER AND HOURS

| Role | Number |
| --- | --- |
| Inspector | 1 |
| NDT technician | 1 |
| Helper | 2 |
| Total | 4 |

Toolbox talk: Pressure testing safety

2. HSE

| Lost time injuries | First aid cases | Near misses |
| --- | --- | --- |
| 0 | 0 | 0 |

3. ACTIVITIES COMPLETED

| No. | Discipline | Activity completed |
| --- | --- | --- |
| 1 | PSV | As-found tests of PSV-101A, 21-PSV-003-2, PSV 18 111-1 |
| 2 | NDT | UT survey of V-201 completed (5 CMLs) |

4. PROGRESS

| Planned (%) | Actual (%) | Variance (%) |
| --- | --- | --- |
| 50 | 45 | -5 |

5. HOLDS AND OBSERVATIONS

| Ref. | Type | Description | Raised | Status |
| --- | --- | --- | --- | --- |
| H-01 | Hold | Boiler internal access – Gas-free certificate required before drum entry. | 08 Oct 2026 | Open |
| O-01 | Observation | Scaffold tag missing at drum level | 08 Oct 2026 | Closed 09 Oct 2026 |

6. PLANNED ACTIVITIES – NEXT DAY

- PSV overhaul and as-left tests

- UT of P-301

7. ISSUES AND CONSTRAINTS

Gas-free certificate for drum entry still awaited (H-01).

8. PHOTOGRAPHS

| Figure 1 – PSV-101A on the test bench | Figure 2 – Boiler B-101 front |
| --- | --- |

| Prepared by | Client representative |
| --- | --- |
| Demo Inspector Date: 09 Oct 2026 | Date: |